## Tasks
id | goal | sprint | effort | depends_on | owner_role | status | acceptance_summary | source_audit
1.1 | 1 | S2 | L | — | frontend | planned | Collapse 6 FE entry points to 2 (Quick Add + Plan & Propose); rubric-helper component shared. | flow-audit.md row #1 / D-85
1.2 | 1 | S2 | S | 1.1 | backend | planned | Add Deprecation headers on /approve, /reject, /end, /revoke, /activate legacy endpoints. | D-89
1.3 | 1 | S2 | S | — | documentation | planned | Document slate reject-all vs assignment reject distinction in canonical-staffing-workflow.md. | D-90
1.4 | 1 | S1 | S | — | frontend | planned | Wire FE button on CaseDetailPage to POST /cases/:id/approve. | D-91
1.5 | 1 | S1 | S | — | frontend | planned | Wire FE button on BudgetTab to POST /projects/{id}/budget-change-requests/{approvalId}/approve. | D-92
1.6 | 1 | S1 | M | — | frontend | planned | Build admin FE for /admin/period-locks consuming existing BE endpoint. | D-93
1.7 | 1 | S1 | M | 8.1 | frontend | planned | /admin/audit-log FE page (DataTable + filters); blocked by tenantId on AuditLog. | D-114 / jtbd A4 RED
1.8 | 1 | S1 | M | — | frontend | planned | /admin/setup post-install control surface (re-runnable migration check). | D-117 / Goal 7 admin-governance
1.9 | 1 | S5 | S | — | frontend | planned | /admin/people/new <Navigate> redirect. | D-86
1.10 | 1 | S5 | S | — | frontend | planned | /timesheets <Navigate> redirect to /my-time. | D-87
1.11 | 1 | S5 | S | — | frontend | planned | /timesheets/approval <Navigate> redirect to /time-management. | D-88
1.12 | 1 | S2 | S | — | documentation | planned | Update D-102 narrative — /staffing-board already redirects; remaining work is drag-write inside /staffing-desk. | D-118
2.1 | 2 | S3 | S | — | backend | planned | Drop orphaned ProjectTag and ProjectTechnology join tables (zero writes). | D-94 / functional-duplication-register §1
2.2 | 2 | S3 | M | — | backend | planned | Replace StaffingRequest.headcountFulfilled cached counter with derived count. | D-95 / functional-duplication-register §2
2.3 | 2 | S3 | S | — | documentation | planned | Verify Project.projectManagerId vs Project.leadPmPersonId — close via DM-2.5/DM-3 or ADR. | D-97 / functional-duplication-register §4
2.4 | 2 | S2 | S | 1.1 | backend | planned | Delete 3 injected-but-unused legacy services (Approve/Reject/Revoke) from assignments.controller.ts. | D-98
2.5 | 2 | S4 | S | — | backend | planned | Deprecate POST /staffing-requests/:id/fulfil (canonical = /proposals/:slateId/pick). | D-100
2.6 | 2 | S2 | S | 5.16 | frontend | planned | Consolidate /admin/dictionaries into /metadata-admin with role-scoped entity-type filter. | D-101
2.7 | 2 | S4 | S | — | frontend | planned | Deprecate /staffing-board once drag-write lands in /staffing-desk Distribution Studio. | D-102
3.1 | 3 | S1 | M | — | backend | planned | Wire outbox producers (≥3 mutation flows); add attemptCount/lastError columns; activate publisher tick. | D-142 / scalability §3(g)
3.2 | 3 | S1 | S | — | backend | planned | Make connection_limit env-driven via DATABASE_POOL_LIMIT; document tuning matrix in docs/ops/scaling-tuning.md. | D-143
3.3 | 3 | Backlog | M | — | backend | backlog | WorkforcePlannerService.applyPlan routes through CreateProjectAssignmentService (audit + transaction wrap). | D-99
3.4 | 3 | Backlog | XL | — | backend | backlog | Split setup.service.ts (696), MyTimePage.tsx (1237), TimesheetPage.tsx (971), workforce-planner.service.ts (1584). | D-150
3.5 | 3 | Backlog | S | — | documentation | backlog | Refine forwardRef cycle count: 5 modules / 3 bidirectional cycles, not "4 modules" (Phase 20c-08). | D-151
3.6 | 3 | Backlog | M | — | documentation | backlog | ADR on dashboard.module.ts shape: keep as presentation hub OR push queries to owning modules. | D-152
4.1 | 4 | S1 | S | — | backend | planned | Verify ProjectRagSnapshot seed coverage; fix portfolio-radiator data path showing 0% Green / 0% Critical. | D-115
4.2 | 4 | S1 | M | — | backend | planned | Widen /work-evidence RBAC self-scope OR relocate into /dashboard/employee + /my-time. Cross-tenant probe must 403. | D-116 / jtbd E4 RED
4.3 | 4 | S1 | S | — | documentation | planned | Document HR > RM dual-role landing precedence; add account.preferredDashboardRoute PlatformSetting per-user override. | D-119
4.4 | 4 | S1 | M | — | backend | planned | Sophia 6-person RM dashboard data shaping fix (0% util while staffing-desk shows 27% fill). | D-120
4.5 | 4 | S1 | M | — | frontend | planned | Replace silent "Insufficient role" inline errors with visible error region or hidden-when-no-role pattern. | D-121
4.6 | 4 | S3 | S | — | frontend | planned | Add DeliveryManagerDashboardPage.test.tsx mirroring the 7 other role-dashboard tests. | D-135 / phase18-standardization-changelog 18-A-09
5.1 | 5 | S2 | M | — | backend | planned | Extract repeated @RequireRoles patterns (24×, 29×, 22×) to src/shared/auth/role-presets.ts named constants. | D-130 step 1
5.2 | 5 | S2 | XL | 5.1 | backend | planned | Drive role-presets from responsibilityMatrix.*.roles PlatformSetting; extend ResponsibilityActionKind to cover read endpoints. | D-130 step 2 / D-158
5.3 | 5 | S3 | L | 5.2 | frontend | planned | Build RolePermissionAdminPage admin UI for tenant role redefinition + custom_role_X creation. | D-159
5.4 | 5 | S2 | L | — | backend | planned | Migrate 9 enums to MetadataDictionary (RiskCategory, RiskStrategy, RiskReviewCadence, MilestoneStatus, LeaveRequestType, ChangeRequestSeverity, RolePlanSource, VendorContractType, VendorEngagementStatus). Expand-migrate-contract per enum. | D-107
5.5 | 5 | S2 | S | 5.4 | backend | planned | Fold risk-review-cadence cadence-to-days into D-107 MetadataDictionary entry as value.days int. | D-128
5.6 | 5 | S2 | S | 5.4 | frontend | planned | Switch RisksIssuesTab + RiskRegister to read entry.displayName; remove enum mappings from labels.ts. | D-131
5.7 | 5 | S3 | S | — | backend | planned | Add Grade TS const at src/shared/lookups/grades.ts mirroring PlatformRole pattern. | D-132
5.8 | 5 | S3 | M | — | backend | planned | Register staffing skill-importance weights (0.5/1.0/2.0) + proficiency match thresholds (1.0/0.6/0.3/0) as 7 PlatformSetting keys. | D-122
5.9 | 5 | S3 | S | — | backend | planned | Register staffing recent-role window (12 months) + recency modifier (1.2) as 2 PlatformSetting keys. | D-123
5.10 | 5 | S3 | S | — | backend | planned | Register AssignmentSlaSweepService pre-breach warning levels (0.5, 0.75) as 2 PlatformSetting keys. | D-124
5.11 | 5 | S3 | S | — | backend | planned | Register AssignmentSlaSweepService risk-score breach threshold (15) as 1 PlatformSetting key. | D-125
5.12 | 5 | S3 | S | — | backend | planned | Register NudgeSweeperService 4 windows (60min sweep, 48h proposal-ack, 72h timesheet, 24h dedup) as 4 keys. | D-126
5.13 | 5 | S3 | S | — | backend | planned | Register ProjectRiskService default probability/impact (3/3) + critical-score threshold (15) as 3 keys. | D-127
5.14 | 5 | S3 | S | — | backend | planned | Register ProjectClosureReadinessService budget variance threshold (>10%) as 1 key. | D-129
5.15 | 5 | S4 | M | — | backend | planned | Customization breadth +5: per-project SLA profiles, per-skill weights, per-org allocation ceiling, per-workflow timesheet lock, industry presets. | D-171
5.16 | 5 | S2 | S | — | frontend | planned | Build /admin/platform-settings admin UI surfacing all PlatformSetting keys with per-tenant override. | synthesis open question / Goal 5
6.1 | 6 | S3 | S | — | frontend | planned | Replace raw <button> at MyTimePage.tsx:821 with DS <Button> ghost/icon variant. Verify CI ratchet at 0. | D-133
6.2 | 6 | S3 | S | — | documentation | planned | DS-5 / MasterDetailLayout decision: schedule Sprint 4–5 OR formally retire in ds-deferred-items.md. | D-134
7.1 | 7 | S2 | M | — | frontend | planned | Split work group (18 routes) into projects, staffing, time, reports. | D-136
7.2 | 7 | S2 | S | — | frontend | planned | Retire governance group; fold /exceptions into reports; resolve /integrations duplicate via D-101. | D-137
7.3 | 7 | S2 | S | 4.2 | frontend | planned | Retire evidence group; fold /work-evidence into reports (after D-116 RBAC widening). | D-138
7.4 | 7 | S2 | M | — | frontend | planned | Split admin group (15 routes) into admin-config, admin-integrations, admin-governance. | D-139
7.5 | 7 | S2 | S | 7.1,7.2,7.3,7.4 | frontend | planned | Update RouteGroup type to 8–9 keys reflecting D-136..D-139. | D-140
7.6 | 7 | S5 | S | — | documentation | planned | Codify or comment implicit "My Work" pseudo-group at SidebarNav.tsx:82-87. | D-141
8.1 | 8 | S0 | L | — | backend | planned | T-01a — add tenantId (NOT NULL FK + RLS) to NotificationChannel/Template/Request/Delivery + IdempotencyKey + IntegrationSyncState + PlatformSetting + AuditLog (8 priority models). | D-153 / real-org §2(a)
8.2 | 8 | S1 | L | 8.1 | backend | planned | T-01b — extend tenantId rollout to long-tail of remaining 60 unscoped models. Cross-ref HARDEN_BRIEF F6. | D-153 long-tail
8.3 | 8 | S1 | M | 8.1 | backend | planned | Repository where-clause tenant-filter ratchet via Prisma middleware extension + CI lint blocking new bypass. | D-154
8.4 | 8 | S0 | L | — | backend | planned | Implement /auth/oidc/login + /auth/oidc/callback using openid-client@6.8.2; consume sso.autoProvisionUsers. | D-155 / real-org §2(h)
8.5 | 8 | S0 | M | — | backend | planned | Extend M365DirectoryAdapter to upsert Person rows on reconciliation. | D-156
8.6 | 8 | Backlog | M | — | backend | backlog | SCIM 2.0 server stub (/scim/Users + /scim/Groups). Defer until first customer asks. | D-157
8.7 | 8 | S0 | S | — | backend | planned | D-160a — quick fix: consume general.fiscalYearStart in financial.repository.ts:216-217. | D-160a
8.8 | 8 | S2 | L | 8.12 | backend | planned | D-160b — new FiscalCalendar + FiscalPeriod entities; reverse-migrate ProjectBudget.fiscalYear:Int → FiscalPeriodId. | D-160b
8.9 | 8 | S0 | M | — | backend | planned | Consume general.timezone + timesheets.weekStartDay; replace getMondayOfWeek(new Date()) with tenant-tz/week-aware helper. | D-161
8.10 | 8 | Backlog | S | — | backend | backlog | Add Region + Country layer to it-company-profile seed; ship enterprise variant for 5,000-person multi-country shape. | D-162
8.11 | 8 | S0 | S | — | backend | planned | PublicHoliday multi-region: drop @default("AU"); accept regionCode[] on public-holiday.service.ts:15. | D-163
8.12 | 8 | S0 | L | — | backend | planned | New FxRate { tenantId, fromCurrency, toCurrency, rate, asOf } model; consolidation in financial.service.ts:61-196 with displayCurrency parameter. | D-164
8.13 | 8 | S0 | M | — | frontend | planned | Consume general.currency in Intl.NumberFormat (drop hardcoded en-US/USD); install date-fns-tz; convert 120 raw new Date() calls. | D-165
8.14 | 8 | S4 | L | — | backend | planned | Bulk-import scope expansion: Project/OrgUnit/Skill/RateCard + XLSX + ImportBatch model + transactional rollback. | D-166
8.15 | 8 | S0 | S | — | documentation | planned | D-96 soft-delete decision: default to archivedAt as live column; deletedAt declared dead weight. Required input to D-167. | D-96 / Goal 8
8.16 | 8 | S1 | L | 8.1,8.15 | backend | planned | POST /admin/persons/:id/forget — redact-payload v1 (set payload.email + payload.actorDisplayName to [redacted] while preserving hash chain). | D-167
8.17 | 8 | S1 | M | — | backend | planned | audit.retentionDays setting + nightly auto-purge cron honoring GDPR Art. 5(1)(e). | D-168
8.18 | 8 | S0 | S | — | documentation | planned | Write GDPR erasure ADR: redact-payload v1 chosen; cryptographic-forgetting v2 backlog ticket. | T-03 ADR / Goal 8
9.1 | 9 | S1 | M | — | backend | planned | Add 12 missing FK indexes (PersonSkill.skillId, TimesheetEntry.timesheetWeekId, ProjectActivationApproval.requestedById, etc.); add CI lint preventing regressions. | D-110 / data-quality Part 4d
9.2 | 9 | S2 | M | — | documentation | planned | Decide actor-audit gap: denormalize createdById/updatedById on rows (cost M) OR formalize "use AuditLog joins" patterns + lint rule. | D-103 / data-quality Part 1 finding 1
9.3 | 9 | S2 | S | — | backend | planned | Add createdAt/updatedAt to ProjectActivationApproval, PersonReleaseApproval, StaffingRequestFulfilment. | D-104
9.4 | 9 | S2 | M | — | backend | planned | Rename 10 booleans to is*/has*/can*/should*/must* prefix (full list in audit Part 2). | D-105
9.5 | 9 | S2 | M | — | backend | planned | Standardize enum casing — AggregateType (26 values) + LocalAccountSource (4 values) → SCREAMING_SNAKE. | D-106
9.6 | 9 | S2 | L | — | backend | planned | Effective-dating uniformity — pick validFrom/validTo OR effectiveFrom/effectiveTo; migrate RateCard + PersonCostRate to Timestamptz(3); add @@unique([parent, ...From]). | D-108
9.7 | 9 | S2 | S | — | backend | planned | Change OnboardingTourProgress.person FK action: Cascade → SetNull. | D-109
9.8 | 9 | S2 | M | — | backend | planned | Add 6–10 Postgres CHECK constraints (allocationPercent 0–100, effectiveTo>effectiveFrom, hoursWorked>=0, headcountFulfilled<=headcountRequired, LENGTH(reason)>=10, workspendSummary IS NOT NULL OR status!=CLOSED). | D-111 / data-quality Part 6
9.9 | 9 | S2 | S | — | documentation | planned | Decide Class E pattern (isActive only) — migrate to archivedAt for analytics, OR document as intentionally simple. | D-112
9.10 | 9 | S2 | S | — | documentation | planned | Document Class F pattern (isActive + archivedAt) on HelpTip/RateCard/RateCardEntry/ResponsibilityRule. Note RateCard financial drift risk. | D-113
9.11 | 9 | S1 | M | — | backend | planned | Top-3 unbounded findMany fix: project-assignment.repository.ts:84, planned-vs-actual-query.service.ts:79, DM dashboard 4× full TimesheetEntry scans. | D-144
9.12 | 9 | S1 | S | — | backend | planned | PvA per-project findUnique loop → findMany({ where: { id: { in: pids } } }) at planned-vs-actual-query.service.ts:382-384. | D-145
9.13 | 9 | S1 | S | — | backend | planned | Hoist workforce-planner.service.ts:625 platformSetting.findUnique outside the 5,000-person loop. | D-146
9.14 | 9 | S2 | XL | 9.1 | backend | planned | Materialized rollup bundle: mv_person_week_utilization, mv_project_week_actuals, mv_project_capitalisation_month, mv_overtime_summary_week, mv_dm_dashboard_aggregates, mv_radiator_history. Refresh via cron. | D-147 / scalability §3(h)
9.15 | 9 | S2 | S | — | backend | planned | Override no-store on /api/admin/skills, /api/metadata/dictionaries*, /api/admin/roles, /api/admin/grades to public, max-age=3600. | D-148
9.16 | 9 | S2 | M | — | backend | planned | ETag interceptor for /api/reports/mood-heatmap + /api/staffing-desk/project-timeline; radiator endpoints to private, max-age=60. | D-149
9.17 | 9 | S4 | L | 9.15,9.16 | backend | planned | Reporting CSV/XLSX export endpoints with cursor pagination + modifiedSince filter for BI tools (Snowflake, Power BI, Tableau). | D-169 / real-org §2(k)
9.18 | 9 | S4 | M | 3.1 | backend | planned | Webhook event-type registry + per-event-type schema documentation; surface at /admin/webhooks/registry. | D-170

## Risk register
id | goal | risk | likelihood | impact | mitigation
R-01 | 8 | T-01 multi-tenant rollout breaks an existing repository at runtime | High | High | Feature-flag rollout; staging soak; CI lint on new repos
R-02 | 8 | Sprint 0 budget over-runs; P0 work slips | Medium | High | Capacity check documents tightness; pre-commit to T-01 split + SCIM defer
R-03 | 5 | ResponsibilityRule reads extension causes silent ACL drift | High | High | FF + staging soak
R-04 | 9 | MV refresh cron causes DB contention | Medium | High | Off-hours schedule; concurrent refresh limit
R-05 | 8 | Redact-payload v1 fails GDPR audit | Low | High | ADR documents v2 cryptographic-forgetting upgrade path
R-06 | 8 | OIDC handler bug allows cross-tenant login | Low | Critical | Integration test for cross-tenant tid claim; manual security review pre-ship
R-07 | 9 | Outbox producers double-fire alongside dual-write seam | Medium | High | flag.outboxEnabled gate; staged rollout
R-08 | 1 | Quick-Add modal collapses information PMs need | Medium | Medium | A/B with 2 PMs; rubric helper component shared
R-09 | 8 | Capacity over-budget triggers ad-hoc descoping mid-sprint | High | Medium | Sprint-level review at S1 mid-point; pre-agreed deferrable list (T-09, T-21)
R-10 | 9 | T-08 D-110 FK indexes deferred → T-13 MVs degrade | Medium | High | Hard sequence in roadmap; T-13 doesn't start until D-110 done
R-11 | 9 | Webhook registry exposes internal event types not meant to be public | Low | Medium | Event-type opt-in registry, not opt-out
R-12 | 1 | Legacy alias redirects break bookmarks | Low | Low | Keep redirects active for 1 release; add Deprecation header
R-13 | 5 | Enum migration breaks existing data | Medium | High | Expand-migrate-contract per enum; CI lint rolls forward
R-14 | 5 | Industry preset switch confuses admins | Medium | Low | Preview mode (dry-run); admin sees diff before commit
R-15 | 6 | DS-5 acceptance hides a future scaling problem | Low | Medium | Document the shape and the trigger condition for revisiting
R-16 | 7 | Retiring evidence ahead of D-116 RBAC widening orphans the route | Medium | High | Hard sequence: D-116 in S1, retire in S2
R-17 | 8 | Adding tenantId to AuditLog breaks the hash chain | Medium | High | Expand-migrate-contract: nullable column → backfill → set NOT NULL after backfill verified
R-18 | 8 | FxRate snapshot at asOf in the past silently mis-attributes spend | Medium | Medium | Document the lookup semantic; alarm when no rate within ±7 days of asOf
R-19 | 8 | fiscalYearStart flip mid-year breaks in-flight rollups | Low | High | Validate that no project has open ProjectBudget rows when admin changes the setting

## JTBD matrix
role | jtbd_id | jtbd_title | status | closing_recommendation | source_audit
admin | A1 | Onboard a new tenant from zero | GREEN | — | jtbd-validation-matrix.md
admin | A2 | Provision a user via /admin/people/new | GREEN | D-86 alias redirect | jtbd-validation-matrix.md
admin | A3 | Set platform configuration | AMBER | 5.16 /admin/platform-settings UI | jtbd-validation-matrix.md
admin | A4 | Investigate audit log | RED | 1.7 build /admin/audit-log page | jtbd-validation-matrix.md
admin | A5 | Re-run setup post-install | AMBER | 1.8 build /admin/setup | jtbd-validation-matrix.md
director | D1 | Approve a strategic project | GREEN | — | jtbd-validation-matrix.md
director | D2 | See portfolio radiator | AMBER | 4.1 fix data path | jtbd-validation-matrix.md
director | D3 | Review delivery health | AMBER | 4.5 silent RBAC errors | jtbd-validation-matrix.md
director | D4 | Approve change requests | GREEN | — | jtbd-validation-matrix.md
director | D5 | Investigate exceptions | GREEN | — | jtbd-validation-matrix.md
hr_manager | H1 | Onboard a new employee | GREEN | — | jtbd-validation-matrix.md
hr_manager | H2 | Approve leave requests | GREEN | — | jtbd-validation-matrix.md
hr_manager | H3 | Review HR dashboard | GREEN | — | jtbd-validation-matrix.md
hr_manager | H4 | Manage HR dictionaries | AMBER | 2.6 + 5.16 | jtbd-validation-matrix.md
hr_manager | H5 | Initiate offboarding | GREEN | — | jtbd-validation-matrix.md
resource_manager | R1 | See team utilization | AMBER | 4.4 Sophia 6-person dashboard fix | jtbd-validation-matrix.md
resource_manager | R2 | Plan resource allocation | GREEN | — | jtbd-validation-matrix.md
resource_manager | R3 | Approve assignments | GREEN | — | jtbd-validation-matrix.md
resource_manager | R4 | Resolve overallocation | GREEN | — | jtbd-validation-matrix.md
resource_manager | R5 | Plan staffing slates | GREEN | — | jtbd-validation-matrix.md
project_manager | P1 | Plan project phases | GREEN | — | jtbd-validation-matrix.md
project_manager | P2 | Place a person on a project | AMBER | 1.1 Quick Add consolidation | jtbd-validation-matrix.md
project_manager | P3 | Manage risks | AMBER | 5.4 + 5.6 enum migration | jtbd-validation-matrix.md
project_manager | P4 | Approve timesheets | GREEN | — | jtbd-validation-matrix.md
project_manager | P5 | Close project | GREEN | — | jtbd-validation-matrix.md
delivery_manager | DM1 | Track delivery KPIs | GREEN | — | jtbd-validation-matrix.md
delivery_manager | DM2 | Approve budget changes | AMBER | 1.5 wire FE button | jtbd-validation-matrix.md
delivery_manager | DM3 | Investigate planned-vs-actual | AMBER | 4.5 silent RBAC errors | jtbd-validation-matrix.md
delivery_manager | DM4 | Approve case decisions | AMBER | 1.4 wire FE button | jtbd-validation-matrix.md
delivery_manager | DM5 | Lock a period | AMBER | 1.6 build admin page | jtbd-validation-matrix.md
employee | E1 | Submit timesheet | GREEN | — | jtbd-validation-matrix.md
employee | E2 | Request leave | GREEN | — | jtbd-validation-matrix.md
employee | E3 | See my assignments | GREEN | — | jtbd-validation-matrix.md
employee | E4 | Log work evidence | RED | 4.2 widen RBAC self-scope | jtbd-validation-matrix.md
employee | E5 | See my profile | GREEN | — | jtbd-validation-matrix.md
dual_role_rm_hr | M1 | Switch between roles | AMBER | 4.3 dual-role landing default | jtbd-validation-matrix.md
dual_role_rm_hr | M2 | Approve as RM | GREEN | — | jtbd-validation-matrix.md
dual_role_rm_hr | M3 | Approve as HR | GREEN | — | jtbd-validation-matrix.md
dual_role_rm_hr | M4 | See unified inbox | GREEN | — | jtbd-validation-matrix.md
dual_role_rm_hr | M5 | See merged dashboards | GREEN | — | jtbd-validation-matrix.md

## Customization debt
id | d_id | layer | title | file_anchor | keys_or_count | task_id | closing_theme
C-01 | D-122 | L1 | StaffingSuggestions skill weights + match thresholds | staffing-suggestions.service.ts | 7 keys | 5.8 | T-10
C-02 | D-123 | L1 | StaffingSuggestions recent-role window + recency modifier | staffing-suggestions.service.ts | 2 keys | 5.9 | T-10
C-03 | D-124 | L1 | AssignmentSlaSweepService pre-breach warning levels | assignment-sla.service.ts | 2 keys | 5.10 | T-10
C-04 | D-125 | L1 | AssignmentSlaSweepService risk-score breach threshold | assignment-sla.service.ts | 1 key | 5.11 | T-10
C-05 | D-126 | L1 | NudgeSweeperService four windows | nudge-sweeper.service.ts | 4 keys | 5.12 | T-10
C-06 | D-127 | L1 | ProjectRiskService default probability/impact + critical threshold | project-risk.service.ts | 3 keys | 5.13 | T-10
C-07 | D-128 | L2 | ProjectRiskService cadence-to-days mapping | project-risk.service.ts | via D-107 dictionary | 5.5 | T-09
C-08 | D-129 | L1 | ProjectClosureReadinessService budget variance threshold | project-closure-readiness.service.ts | 1 key | 5.14 | T-10
C-09 | D-130 | L0+→L1 | Repeated @RequireRoles patterns (24×, 29×, 22×) | various controllers | 3 patterns | 5.1+5.2 | T-04
C-10 | D-131 | L2 companion | Frontend risk-enum display labels | RisksIssuesTab.tsx, RiskRegister.tsx | via D-107 | 5.6 | T-09
C-11 | D-132 | TYPE-SAFETY | Grade TS const for type-safe DTOs | src/shared/lookups/grades.ts (new) | G7..G14 | 5.7 | T-09
C-12 | D-107 | L2 | 9 enums → MetadataDictionary | prisma/schema.prisma | 9 enums | 5.4 | T-09
C-13 | D-101 | L2 | Consolidate /admin/dictionaries into /metadata-admin | frontend/src/routes/admin | — | 2.6 | T-09
C-14 | D-158 | RBAC L1 | ResponsibilityRule extended to read endpoints | ResponsibilityActionKind enum | 330 invocations | 5.2 | T-04
C-15 | D-159 | RBAC L1 | Tenant role redefinition admin UI | RolePermissionAdminPage (new) | — | 5.3 | T-04
C-16 | D-171.1 | L1 | Per-project SLA profiles | assignment-sla.service.ts | — | 5.15 | T-10
C-17 | D-171.2 | L1 | Per-skill matching weights | platform-settings.service.ts | — | 5.15 | T-10
C-18 | D-171.3 | L1 | Per-org allocation ceiling | hr-manager-dashboard-query.service.ts | — | 5.15 | T-10
C-19 | D-171.4 | L1 | Per-workflow timesheet lock window | platform-settings.service.ts | — | 5.15 | T-10
C-20 | D-171.5 | L1 | Industry presets seed (Finance/Healthcare/Tech/Public-Sector) | seed json (new) | 4 profiles | 5.15 | T-10
C-21 | D-160 | L1+L2 | Tenant fiscalYearStart consumed; FiscalCalendar entity | financial.repository.ts:216-217 | — | 8.7+8.8 | T-05
C-22 | D-161 | L1 | Tenant timezone + weekStartDay propagation | pulse.service.ts:14-22, 41 | — | 8.9 | T-07
C-23 | D-163 | L1 | PublicHoliday tenant/region scoping | public-holiday.service.ts:15 | — | 8.11 | T-07
C-24 | D-164 | L0+L1 | FxRate model + multi-currency consolidation | financial.service.ts:61-196 | — | 8.12 | T-06
C-25 | D-165 | L1 | Frontend currency formatter wiring + date-fns-tz adoption | BudgetCapexOpexSummary.tsx:15, VendorEngagementPanel.tsx:11 | 120 raw new Date() | 8.13 | T-07
C-26 | D-119 | L1 | HR > RM dual-role landing default override | useAuth() resolver | 1 key per user | 4.3 | T-20
C-27 | D-167 | COMPLIANCE | GDPR right-to-erasure strategy choice | TBD admin endpoint | redact-payload v1 | 8.16 | T-03
C-28 | D-168 | COMPLIANCE | AuditLog retention policy | platform-settings.service.ts | 1 key | 8.17 | T-03
C-29 | D-95 | L2 cleanup | Replace headcountFulfilled cached counter with derived | StaffingRequest aggregate | — | 2.2 | T-19
C-30 | D-103 | L1+L2 | Actor-audit gap (createdById/updatedById) decision | prisma/schema.prisma | 105 models | 9.2 | T-08
C-31 | D-112 | L1 | Class E (isActive only) decision | Client/Tenant/Vendor models | — | 9.9 | T-08
C-32 | D-113 | L1 | Class F (isActive+archivedAt) documentation | HelpTip/RateCard/RateCardEntry/ResponsibilityRule | — | 9.10 | T-08

## HARDEN coverage
harden_or_prior_id | title | closed_or_extended_by | status | notes
F1 | Outbox dual-write seam | HD-7 (closed) + T-11 D-142 wiring | extended | Schema landed; T-11 wires producers + activates publisher
F2 | Outbox publisher | HD-7 (skeleton) + T-11 D-142 | extended | Skeleton in repo; producers + dispatch zero-wired today
F3a | Export primitive | HD-8 chunk 8.1 (closed) | closed | ExportButton component shipped 2026-05-04
F5.1 | Assignment SLA sweep | HD-10 (closed) | closed | Sweep + breach + pre-breach all live
F5.2 | SLA pre-breach warnings | HD-10 (closed) | closed | 50% / 75% pre-breach landed
F6.1 | Tenant column NOT NULL flip (25 scoped models) | HARDEN-owned | in-flight | HARDEN keeps the 25 scoped models; T-01 covers the 80 unscoped
F6.2 | RLS enable on scoped models | HARDEN-owned | in-flight | —
F6.3 | Cross-tenant probe tests | HARDEN-owned | in-flight | —
F9 | Nudge sweep | HD-8 chunks 8.1+8.3 (closed) | closed | —
F11 | Undo seam | HD-8 chunks 8.2+8.4a+8.4b (closed) | closed | UndoModule + 3 destructive actions wired
F15 | Undo FE toast | HD-8 chunk 8.4b (closed) | closed | —
HD-4 | ResponsibilityRule for mutations | closed (6 services) | extended | T-04 D-158 extends to read endpoints
HD-5 | Person release request flow | closed | closed | —
HD-7 | OutboxEvent skeleton | closed | extended | T-11 D-142 wires producers
HD-8 | Help center + nudge + undo + export | closed | closed | —
HD-9 | Help Center MVP | closed (5 chunks) | closed | —
HD-10 | SLA pre-breach warnings | closed | extended | T-10 D-124 makes warning levels tenant-configurable
HD-11 | prom-client + /metrics | closed | closed | —
HD-12 | PlatformFlagsService | closed | extended | T-10 consumes the typed registry for ~21 new keys
HD-13 | RM dashboard split | closed | closed | —
WO-6 | Legacy assignment endpoint deprecation | in-flight | extended | T-16 D-89 adds Deprecation headers as transition
DM-2.5 | publicId rollout | in-flight | referenced | T-19 D-97 verifies before action; T-09 D-130 mirrors PlatformRole pattern
DM-3 | PM relation canonical | in-flight | referenced | Phase 11 should re-verify D-97 before sprint slotting
DM-R-11 | Migration orphan recovery | closed 2026-05-01 | closed | —
Phase 20c-08 | forwardRef cycles | open | refined | T-15 D-151: 5 modules / 3 cycles, not "4 modules"
Phase 20c-12 | Unbounded findMany | open | closed by | T-12 D-144 closes top-3 of 9 unbounded calls
Phase 20c-15 | God page split | open | distinct | T-15 D-150 covers backend + non-dashboard pages
S-05 | ResponsibilityRule consolidation | open | referenced | Folded into T-04 D-130 step 3
S-13 | StaffingRequest derived counters | open | referenced | T-19 D-95 candidate to fold into S-13 scope
D-02 | DI fix | REFUTED | — | —
D-04 | Legacy assignment endpoints | referenced | — | D-89 adds Deprecation header transition
D-09 | Effective-dating cost-rate joins | open | referenced | T-13 D-147 + T-08 D-108 cover
D-10 | Project tag/tech consolidation | superseded | — | Half-wrong per Phase 2; T-19 D-94 drops join tables
D-11 | StaffingRequest status drift | open | referenced | T-19 D-95 candidate to fold
D-27 | Breadcrumb leak | REFUTED | — | —
D-28 | Page title | REFUTED | — | —
D-29 | Locale | REFUTED | — | Phase 9 D-161 supersedes for tenant timezone/week
D-47 | Event silence on create | REFUTED | — | —
D-55 | Radiator cold-start | open | referenced | T-13 D-147 mv_radiator_history covers
D-59 | Audit silence on activate | REFUTED | — | —
D-68 | Cmd+K people | REFUTED | — | —
D-72 | Planner read-only | REFUTED | — | —